## Sheet1
Agile Product Backlog
Task Name | Story | Sprint Ready | Priority | Status | Story Points | Assigned to Sprint
Sprint 1 | No | No | High | Complete | 65 | No
Kaarten maken memory game | Yes | Yes | Medium | Complete | 5 | Yes
UI maken voor memory game | Yes | Yes | Medium | Complete | 10 | Yes
MainCard script maken | Yes | Yes | Medium | Complete | 20 | Yes
SceneControler script maken | Yes | Yes | Medium | Complete | 20 | Yes
Reset knop toevoegen | Yes | Yes | Medium | Complete | 5 | Yes
Score toevoegen | Yes | Yes | Medium | Complete | 5 | Yes
Einde memory game toevoegen | Yes | Yes | Medium | Complete | 15 | Yes
Introductiescherm memory toevoegen | Yes | Yes | Medium | Complete | 2 | Yes
Sprint 2 | Yes | Yes | Medium | Complete | 41 | Yes
Vragen verzinnen voor quiz | Yes | Yes | Medium | Complete | 5 | Yes
GameManager Script maken | Yes | Yes | Medium | Complete | 20 | Yes
Qeustion script maken | Yes | Yes | Medium | Complete | 6 | Yes
Animaties toevoegen | Yes | Yes | Medium | Complete | 10 | Yes
Introductiescherm quiz toevoegen | Yes | Yes | Medium | Complete | 2 | Yes
Main Menu toevoegen | Yes | Yes | High | Complete | 5 | Yes
Sprint 3 | Yes | No | Medium | In Progress | 110 | Yes
Einde toevoegen quiz | Yes | Yes | Low | In Progress | 15 | Yes
Overkoepelende punten toevoegen | Yes | Yes | Medium | In Progress | 30 | Yes
High-score toevoegen | Yes | Yes | Medium | Complete | 40 | Yes
Achtergrond muziek toevoegen | Yes | Yes | Medium | Complete | 15 | Yes
Nieuwe minigame concept opzoeken | Yes | Yes | Medium | In Progress | 10 | Yes
Sprint 4 | Yes | No | Medium | In Progress | 0 | Yes
Falling words opzet | Yes | Yes | Medium | Complete | 41 | Yes
Woordenlijst maken | Yes | Yes | Medium | Complete | 32 | Yes
Woorden Highlighten bij overtypen | Yes | Yes | Medium | Complete | 32 | Yes
Woord snelheid toevoegen | Yes | Yes | Medium | Complete | 40 | Yes
Einde Quiz | Yes | Yes | Medium | Complete | 51 | Yes
Backlog | Yes | Yes | Low | Not Started | 0 | Yes
Store toevoegen | Yes | No | Low | Not Started |  | No
Loading Screen | Yes | No | Low | Not Started |  | No
Pauze scherm toevoegen | Yes | No | Low | Not Started |  | No
"victory" geluidseffect toevoegen | Yes | No | Low | Not Started |  | No
Speler data opslaan | Yes | No | Low | Not Started |  | No

## Sheet2
This sheet is to enable the drop-down lists
Yes | High | Complete
No | Medium | In Progress
| Low | Not Started